## Main Action Plan
|  | Legend: | Initially planned activity of co-creative work
Extended activity of co-creative work
Implemented as initially planned
Revised international mobility
New proposals agreed by partners
|  |  | Did not happen as it was initially planned |  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
Converted from F2F to online
| - |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
WP |  | Outputs | Sub-outputs | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2020-11-23 | 2020-12-23 | 2020-01-24 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01
Preparation | WP1-Preparation (ISEE-HSP) | 1.1 Kick-off seminar and reaching common understanding | 1.1.1. Mobility 1: Kick-Off Meeting 1.1.1.1. Gantt Chart 1.1.1.2. Project Branding 1.1.1.3. Presenting Key-Concepts 1.1.1.4. Mobility Plan 1.1.1.5. Establish Quality Assurance Team 1.1.1.6. Establish Project Management Group 1.1.2. Shared Understanding for Reaching Results
Mobility 0: Participation in the Workshop for Project Coordinators and Partner Country institutions in Brussesls
|  |  | Mobility 1: Kick-Off Meeting Proposed to be converted into Mobility 6: Training for the Kosovo staff and students | 2021-02-01: ONLINE | [17 empty] | Converted into an Extra training for Kosovo Teachers and Professionals for e-health and e-rehabilitation services Related to mobility 6 5 - 9 June 2023
|  | 1.2 Establishing and maintaining the project website | 1.2.1 Establish the Project Website
|  | 1.3 Co-defining common understanding of key concepts (Online workshop) | 1.3.1. Handbook of Key Concepts
Development | WP2-Operating Model (Metropolia) | 2.1 Investigating and sharing good practices of existing digital learning centres. | 2.1.1. Investigating Similar Digital Centres in Finland and Europe (Metropolia)
|  |  | Mobility 2: Study Visit in Finland/Metropolia | 2021-04-01: ONLINE | [15 empty] | 1-5 May 2023
|  | 2.2 Designing the business plan of the SIAHDPC based on the key concepts, including: Person-involvement, interdisciplinary and transdisciplinary, service design and (distance) co-creation. | 2.2.1. Design the Business Plan 2.2.2. Usability and Effect Assessment of The Centre for Learning Purposes 2.2.3. Prepare E-Health and E-Rehabilitation Services
|  | 2.3 Establishing the digital platform of the Virtual Clinic | 2.3.1. Organogram 2.3.2. Terms of Reference 2.3.3. Establish the Space and Equipment Plan of the Centre 2.3.4. Functionalization of the Virtual Clinic 2.3.5. Identification of the Main Stakeholders and Target Groups
|  |  | Mobility 3: Tutoring Workshop in Helsinki | 2021-10-01: ONLINE | [28 empty] | 18-22. March 2024
|  | 2.4 Integrating the SIAHDPC with other centres of (non) project partners | 2.4.1. Investigating and Establishing a Partnership with Similar International Digital Centres
|  | 2.5 Simulated Piloting | 2.5.1. Simulation Piloting
|  | 2.6 Online tutoring and online workshop | 2.6.1. Online Tutoring (Bi-weekly Meetings)
|  | 2.7 Evaluation and adjustment | 2.7.1. Webinar of the Digital Pedagology 2.7.2. Co-creation of the Digital Pedagogy
| WP3-Teachers' Competencies (MLU-Halle) | 3.1 Developing the teacher’s Toolkit learning pedagogical approaches based on digital technologies | 3.1.1. Enhance Competencies in Modern Pedagogical Approaches based on Virtual reality 3.1.2. Teachers' Toolkit co-creation
|  | 3.2 Developing teachers’ competences to empower them for using digital technologies | 3.2.1. Teachers' Pedagogical Competence related to the SIAHDPC Digital Competences 3.2.2. CPD Course Development (1 Course) 3.2.3. Curriculum Review in order to integrate Digitalization (Teachers' Toolkit preparation) 3.2.5. Online Tutoring Workshop: Modern Educational methods and development of VR-based Courses, and Teaching/learning Materials 3.2.6. Online Reflective Workshop
|  |  | 3.2.4. Mobility 4: Study Visit to Halle | 2021-11-01: 7-13/11/2021
|  |  | 3.2.7. Mobility 7: Post-Pilot Reflective Seminar in Halle | [35 empty] | 04-08 Dec 2023
|  | 3.3 Providing the teacher's training on pedagogical approaches based on digital technologies (training the trainers) | 3.3.1. Enhance Competencies in Utilizing Digital Technologies in Teaching and Research 3.3.2. Digitalization Training for Teachers'
|  |  | Mobility 5: Teachers' Training in Prishtina (pedagogical Approaches) | [14 empty] | 28.03-01.04.2022
|  | 3.4 Developing the Roadmap (Guideline) for the development of virtual therapy, remote and tele-health services | 3.4.1. Developing and Delivering Virtual Therapy, Remote and Tele-health Services 3.4.2. Co-developing the Guideline (methodogical Framework that facilitates the transfer of acquired knowledge to the work Environment and how to safe-guard the user involvement)
|  | 3.5 Providing the teacher's training on designing and delivering eHealth and eRehabilitation services | 3.5.1. Build Competencies of the HEI Staff for developing and delivering virtual therapy and remote tele-health services
|  |  | Mobility 6: Teachers training in Prishtina (Designing E-Health and E-Rehabilitation Services) | [17 empty] | 12-16.09.2022
|  | 3.6 Evaluation and adjustment | 3.6.1. Identify Areas of Improvement
| WP4- Students' Competencies (JAMK) | 4.1 Investigating and co-working through best practices | 4.1.1. CPD Course Development 4.1.2. Carpe Diem Workshop Pre-Meeting 4.1.3. Digital Competence Handbook | bar: 2021-03-01 to 2021-12-01
|  |  | Mobility 8: Study Visit in Finland (JAMK) Carpe Diem Workshop) | [15 empty] | 25-29.04.2022 | bar: 2021-12-01
|  | 4.2 Developing CPD and on-line learning materials and utilising virtual learning | 4.2.1. Co-creating a Carpe Diem CPD Course Prototype 4.2.2. Update 6 existing CPD Courses 4.2.2.1. Innovation and Entreprenership 4.2.2.2. Interdisciplinary Collaboration 4.2.2.3. Evidence-Informed Practice 4.2.2.4. User-Involvement 4.2.2.5. Person- Centreredness 4.2.2.6. ICT & Digital Competence 4.2.3. Co-create 3 CPD Courses 4.2.3.1. Interdisciplinary Collaboration 4.2.3.2. Evidence-Informed Practice 4.2.3.3. User-Involvement and Person-Centeredness
|  | 4.3 Piloting CPD courses | 4.3.1. CPD Course Piloting by the Kosovar HEIs (teacher-student mentoring) 4.3.2. Check-reality to test the teachers' Digital Skills
|  | 4.4 Evaluation and adjustment | 4.4.1 Evaluation and adjustment
Quality | WP5-Quality Plan (RIT-K) | 5.1 Establishment of internal evaluation team | 5.1.1. Evaluation Team Establishment
|  | 5.2 Co-construction of the quality plan | 5.1.2. Quality Plan
|  | 5.3 Regular evaluations (every three months) | 5.3.1. Regular Meetings
|  | 5.4 External evaluation | 5.4.1. Interim Report 5.4.2. Erasmus+ Agency Evaluations
Dissemination | WP6-Dissemination and Exploitation (UKZ) | 6.1 Continuous networking | 6.1.1. Mobilities 6.1.2. Relevant Conferences (WP2 & WP4)
Mobility 11: International Conferences in Germany (EU)
Mobility 12: International Conferences in Finland (EU)
|  | 6.2 Sustainability | 6.2.1. Dissemination Plan & Sustainability Strategy 6.2.2. JVG and IAB Structures
|  | 6.3 Dissemination seminars | Mobility 9: Interim Dissemination Seminar in Prishtina | [20 empty] | 15-18 Sep 2022
|  |  | Mobility 10: Final Dissemination Seminar in Prishtina | [44 empty] | 12 and 13th of Sep 2024
Management | WP7-Management (HC) | 7.1 Launching of the project and managing | 7.1.1 Designing the work plan based on the SMART principles 7.1.2. Action Plan 7.1.3. Mobility Plan 7.1.4. Budget 7.1.4.1. Suc-Contracting 7.1.4.2. Travel & Stay Costs 7.1.4.3. Transfers to Partners 7.1.5. Reporting
|  | 7.2 Student Interdisciplinary Operational Team | 7.2.1. Student Monthly Meetings
|  | 7.3 Project management group meetings | 7.3.1 Monthy PMG Meetings
|  |  | Mobility 13: Project Managament Meeting in Helsinki | [41 empty] | 17-18 June 2024
Mobility 15: Project Managament Meeting in Halle
|  |  | Mobility 17: Project Managament Meeting in Prishtina | [40 empty] | 28-29 May 2024
|  | 7.4 Steering group meetings | 7.4.1 Every 6 Months Meetings
|  |  | Mobility 14: Steering Committee Meeting in Helsinki | [41 empty] | 17-18 June 2024
Mobility 16: Steering Committee Meeting in Halle
|  |  | Mobility 18: Steering Committee Meeting in Prishtina | [40 empty] | 28-29 May 2024