## Sheet1
Legend
Completed as planned
Postponed
New itineraries proposed
No need for change
SIAHDPC Project
| WP1 | Event | Initial plan | New plan 1.0 | New Plan for 3 years | New plan for years 3.8 | New plan
|  | Mobility 1: Kick-Off Meeting | 15,18,22,23 Feb 2021 (Online) | - |  |  | "Converted into an Extra training for Kosovo Teachers and Professionals for e-health and e-rehabilitation services Related to mobility 6 5 - 9 June 2023 "
| WP2 | Mobility 2: Study Visit in Finland/Metropolia | 12,13,20,21,26 April 2021 (Online) | Oct or Nov 2022 in parallel with PMG and SC meeting in Helsinki | 30th April - 6th of May | 1-5 May 2023
|  | Mobility 3: Tutoring Workshop in Helsinki | 31 Jan- 03 Feb 2022 (Online) | April or May 2023 | 2023-06-01 | 2024-05-01 | 18-22. March 2024
| WP3 | Mobility 4: Study Visit to Halle | 07-13 Nov 2021- Halle, Germany | - | - | -
|  | Mobility 5: 1st Teachers' Training in Prishtina (pedagogical Approaches) | 27 March- 02 April 2022, Prishtina, Kosova | - | - | -
|  | Mobility 6: 2nd Teachers training in Prishtina (Designing E-Health and E-Rehabilitation Services) | 2022-06-01 | 11-17 Sep 2022, Prishtina, Kosova | - | -
|  | Mobility 7: Reflective Seminar in Halle | 2022-03-01 | June 2023 - in parallel with PMG and SC meeting in Halle - Proposal: June 2023 | 2023-07-02 | 2023-10-01 | 04-08 Dec 2023
|  | Unplanned: Mobility 19: 3rd Teachers Training in Prishtina or Reflective workshop (Parallel with the summer school) | - | - |  | 2023-06-01
| WP4 | Mobility 8: Study Visit in JAMK Finland (Carpe Diem Workshop) | 14.-15.12.2021 (online study visit) | 24-30 April 2022, Jyvaskula, Finland | - | -
| WP6 | Mobility 9: Interim Dissemination Seminar in Prishtina | 2022-10-01 | 15-18 Sep 2022, Prishtina, Kosova | - | -
|  | Mobility 10: Final Dissemination Seminar in Prishtina | Sep 2023 - in parallel with PMG meeting in Pristina - Proposal: September 2023 | 16-18 Sep 2023 | 2023-09-01 | 2024-06-01 | 12 and 13th of Sep 2024
|  | Mobility 11: International Conferences in Germany (EU) | Despite being approved initially, these will have to be cancelled! Partners plan to utilize them by providing the opportunity to additional team members to participate in the authorised international mobilities.
Mobility 12: International Conferences in Finland (EU)
| WP7 | Mobility 13: Project Managament Meeting in Helsinki | 2022-02-01 | Oct or Nov 2022 | 2023-12-01 | 2024-01-01 | 17-18 June 2024
|  | Mobility 14: Steering Committee Meeting in Helsinki | 2022-02-01 | Oct or Nov 2022 | 2023-12-02 | 2024-01-01 | 17-18 June 2024
|  | Mobility 15: Project Managament Meeting in Halle | 2022-10-01 | 2023-06-01 | 2023-07-01 | 2024-03-23
|  | Mobility 16: Steering Committee Meeting in Halle | 2022-10-01 | 2023-06-01 | 2023-07-02 | 2024-03-23
|  | Mobility 17: Project Managament Meeting in Prishtina | 2023-09-01 | - | 2023-09-01 | 2024-06-01 | 28-29 May 2024
|  | Mobility 18: Steering Committee Meeting in Prishtina | 2023-09-01 | - | 2023-09-01 | 2024-06-01 | 28-29 May 2024
| Unplanned | Mobility 20: Digital Innovations for the Future Housing of Seniors in Helsinki |  | 2022-09-01